Mission: Creating Policy and System Change for Independent Living.

Vision: To Influence policy and access to service delivery for all individuals with disabilities in California.

Goal Name: 2020-2021 SPIL Amendment Evaluation

Goal Description: Review & evaluate the progress made in 2020-2021 SPIL Amendment

**Activity: Monitor, review, & evaluate the implementation of the 2020-2021 SPIL**

 **Amendment**

Inputs: Committee/ staff/stakeholder: wisdom, analysis, meetings; data gathered related to subject; SILC office equipment and materials; SILC website.

Outputs:

1. Monthly SPIL Committee meetings review progress.
2. Formulate SPIL evaluation tool.
3. New/original data collected.
4. Analysis of data.
5. Quarterly reports to full council.
6. SPIL evaluation annual report
7. Findings reported: A completed report summarizing the results.

Effects/Results/Consequences/outcome/impact

1. Consistent monitoring and reporting will increase accountability.
2. SILC and I.L. Network will have information about what strategies were effective from 2020-2021 SPIL to guide them in crafting the 2024-2027 SPIL.

Goal Name: 2021-2023 SPIL Implementation

Goal Description: Monitor, review, & evaluate the implementation of the 2021-2023 SPIL

**Activity: Monitor, review, & evaluate the implementation of the 2021-2023 SPIL**

Inputs: Committee/ staff/stakeholder: wisdom, analysis, meetings; data gathered related to subject; SILC office equipment and materials; SILC website.

Outputs:

1. Monthly SPIL Committee meetings review progress.
2. Formulate SPIL evaluation tool.
3. New/original data collected.
4. Analysis of data.
5. Quarterly reports to full council.
6. Continue workgroup activities – ILC database survey; LTSS ILC-ADRC Environmental Scan survey
7. SPIL evaluation annual report (year 1 SPIL) (November 2021 meeting)
8. Statewide needs assessment
9. SPIL evaluation annual report (year 2 SPIL) (November 2022 meeting)
10. Findings reported: A completed report summarizing the results and recommendations for the 2024-2027 SPIL. (Early 2023 meeting)

Effects/Results/Consequences/outcome/impact

1. Consistent monitoring and reporting will increase accountability.
2. SILC and I.L. Network will have information about what strategies were effective from 2021-2023 SPIL to guide them in crafting the 2024-2027 SPIL.

**Activity: Statewide ILC consumer satisfaction survey report**

Inputs: ILCs: Reports of most recent annual Consumer Satisfaction Survey. Committee/ staff/stakeholder: wisdom, analysis, meetings; data gathered related to subject; SILC office equipment and materials; SILC website;

Outputs:

1. Outreach to all Independent Living Centers in California to obtain most recent annual Consumer Satisfaction Survey (April 2022)
2. Analysis of data received, preliminary report (May 2022 meeting)
3. SPIL Committee recommendations for report out to state I.L. Network (May 2022 meeting)
4. Finalized publication to share (July 2022 meeting)

Effects/Results/Consequences/outcome/impact

1. Detailed knowledge about existing consumer satisfaction survey system.
2. Recommendations to share with DOR and the I.L. Network to build on this knowledge.
3. Information that can be used to craft the 2024-2027 SPIL.